## BU HR EiR Actions 2019-21
Reporting Template for BU Research Concordat Actions 2019-21
Action Ref | Detail | Target Date and Success Measures | Owners | Lead and Reporting owner | Consolidated Update (2019-2020)
GEN1 | To hold regular Concordat-themed meetings with research staff and their line managers to discuss the action plan and generate feedback and further ideas. | Target date: Spring - Summer 2020 for Vitae meeting, with others ongoing Success measures: Aim for at least 75% of attendees to have found each event good or above A meeting will be arranged with Vitae in 2019/2020, as per the meeting held on 27/04/18. The Concordat will be discussed within RSA meetings, the Early Career Researcher Network and, additionally, a forum has been set up within the ECRN Community on Brightspace (BU's VLE). In the context of the Concordat's Seven Principles, there will be a meeting specifically to consider these at least annually and, once the Concordat review and consultation has been concluded, there will be opportunities to discuss the revised Concordat. | RCSG | Theresa McManus | Regular meetings (latterly on-line) have been held via the Research Staff Association and the Early Career Researcher Network in order to create and sustain a dialogue around the Concordat themes, e.g. access to appropriate training, research funding, mentoring and employment contracts. Some events have been specifically about the Concordat. On average, appropriately 10 staff attend each event. Feedback which staff have provided to the RCSG, especially from those new to research careers, show that staff have found it an invaluable source of information and support as well as being useful for networking. We had been planning a major event around a visit from Vitae in 2020, but this has now been postponed owing to the outbreak of the C19 pandemic. Insight from RSA representatives at our RCSG has informed future action planning - for example the need to ensure that appraisals are taking place on a regular basis as agreed, and the need to introduce a framework for mentoring to ensure consistency across faculties. See ECI1 in new action tracker.
GEN2 | To ensure the Concordat is a standing agenda item at the FRPPCs and that matters raised are suitably discussed at URPPC. To provide support to the Faculties to address any issues arising and embed knowledge of the Concordat principles as appropriate. | Target date: Ongoing, monitored annually Success measures: 100% compliance To monitor meeting attendance and minutes with 100% compliance expected on meeting agendas. | RCSG (all) and DDRPPs | Rebecca Edwards | The Concordat is a standing agenda item on all the faculty's FRPPC meetings, evidenced by agendas and minutes (DDRPPs report 100% compliance). Faculty reps have reported on Research Staff Association activities around the Research Concordat to the FRPPC. See EC2 in new action tracker.
A.1.0c | To implement a more robust, transparent and accessible means of identifying current research staff as a cohort (to include pertinent information for monitoring, such as contract end dates, line managers, etc.). This links to Action B.2.4b. | Completed With the implementation of the new HR system (iTrent) any further developments will result in a mirroring or improvement of the current provision, which will be reported to RCSG. | RDS, HR and Faculties | Elaine Sheridan | New reports have been developed in the new HR system. Reporting on statistics relating to research staff are provided for RCSG meetings; reports identifying research staff are produced quarterly for RSA reps, and are also available on request. Through more accurate identification of research staff, this has enabled targeted updates to be provided to the relevant community and for RSA staff to engage directly with researchers in their Faculty. Furthermore, this data can now be used for comparison purposes in undertaking equalities analysis (for example, we can now see that 80% of research staff are homed in departments that have been awarded a bronze Athena Swan award).
A.1.2a | Review career framework for research staff posts including standard job descriptions, person specifications, pay and grading. (The RCSG will have the opportunity to feed into this review. Once ratified, development opportunities will be reviewed, refreshed and aligned to the Framework/Fusion to assist staff in advancing their careers.) | Target date: TBC - This is an identified work stream under BU2025 which needs to be scope and timeline agreed. Success measures: Implementation of a career framework | HR | Elaine Sheridan | The career framework for research staff has been on hold due to COVID-19. However we do now have standardised job descriptions for research staff. See EI1 in new action tracker.
A.1.2b | To ensure employment procedures are updated in light of Brexit and legislative changes (for example, changes to Tier 2 sponsorship). | Target date: As per Brexit and associated requirements Success measures: 100% compliance HR will ensure compliance, as required, following the conclusion of Brexit negotiations and any transition period | HR | Elaine Sheridan | Employment procedures updated. HR continuing to review these procedures as further guidance is forthcoming. See EI1 in new action tracker
A.1.3a | To continue to review the proportion of research staff on fixed-term contracts, particularly those on hourly paid and/or successive short-term contracts. To review how the BU Code of Practice – Use of Fixed-Term Contracts (and associated procedural documentation) is implemented. | Target date: Ongoing, with quarterly reports to RCSG Success measures: Improved satisfaction / feedback via the CROS and PIRLS survey BU aims to ensure that all research staff are employment and research ready, if this employment is within BU or elsewhere. This forms part of the overall BU workforce planning processes, with the BU CoP Use of Fixed-Term Contracts, scheduled for review in January 2019 | HR | Elaine Sheridan | HRMs are working with faculties to ensure most appropriate methods for appointment considered, seeking to provide continuity of employment where possible and looking at suitable alternative employment in the event that FTC is used upon its cessation. Although formal reviews have been delayed, there is a bridging fund in place to facilitate employment continuation during short intervals between contracts. This has been used 15 times in the last 2 years. BU is seeking to avoid FTC as appropriate. BU will continue to review the use of FTC and only use where essential. As of April 2021, 86% are on fixed-term contracts, the remainder on established contracts. This is slightly down from the figure reported in CROS in 2019 (89.2% against a national average of 63.8%). It is recognised that this is a very high proportion compared nationally, and therefore, reviewing researcher career pathways - including contracts - is a core action for the future action plan. See EI5 in new action tracker.
A.1.4a | To implement the e-Recruitment module and undertake monitoring to ensure interview panels reflect diversity and experience/expertise. | Target date: June 2019, revised to May 2020 for system implementation with monitoring via panel checklist Success measures: Implementation and 100% compliance with panel composition requirements A tender is currently in progress to meet this action's requirements. It is anticipated that the system will be operational by May 2019 | HR | Elaine Sheridan | A new HR system has been implemented. The E-Recruitment module is currently TBC, given the rephasing of projects due to COVID-19. See EI5 in new action tracker.
B.2.1a | Review the contractual status of research staff. The RCSG will have the opportunity to feed into this review (Externally facing opportunities to differentiate this action from that of C.3.7) | Target date: TBC - This is an identified work stream under BU2025 which needs to be scope and timeline agreed. Success measures: Implementation of a career framework | HR | Elaine Sheridan | This action has been on hold due to COVID-19. See EI5 in new action tracker.
B.2.1d | To continue to support and resource the RSA and to see how stronger links with other BU staff/departments could be forged with the RSA. To clarify and promote the roles of the BU Research Staff Representatives. To ensure research staff have, and know they have, a voice at URPPCs, FRPPCs and RCSG. To survey the RSA constituency to understand the types of activities that will interest and engage them, and build this into the RSA’s plan of activities. | Target date: Summer 2019 (CROS19) Success measures: CROS19 to show that at least 30% of research staff are actively engaging with the RSA and find the engagement beneficial, with at least 75% of survey respondents being positive (satisfactory or above) about RSA activities within this action RDS is working closely with the RSA, especially new representatives, to promote and advance their activity and voice within BU. Further actions are to be identified as a result of CROS19 and to be added to the action plan. | University Research Staff Reps | Chris Stantis and Michelle Heward | RDS continue to provide administrative support for the RSA. This includes maintaining governance documents, ensuring vacancies are filled, forging links with other groups with similar interests e.g. the ECR Network and union staff representing research staff, and assisting with developing communication plans to facilitate more interaction with other research staff. Although the early retirement of the post holder concerned has meant RSA satisfaction has not been surveyed, attendance at RSA meetings has steadily improved and the reps are taking a much more active role to ensure that research staff engage with the network, for example organising drop-in coffee mornings for research staff. Discussions are currently underway to develop a plan for improving engagement of research staff with the RSA. Research staff via their RSA reps are much more visible now in the Faculty Research and Professional Practice Committee meetings, and feel that their interests are supported. University RSA reps also attend the University Research and Professional Practice Commitee meetings, providing updates on research staff matters. Research staff have been identified as a key group to support through the COVID-19 crisis: minimal numbers of research staff (and only in the interest of the project) have been placed on furlough - with BU supplementing their salary to ensure there is no financial penalty. Furthermore, the limited access to research sites has been prioritised for projects where research is tied to external funding, seeing researchers prioritised to return to the laboratories where space is limited (and ahead of full campus re-opening). See EI6 in new action tracker.
B.2.1e | To improve the dedicated RSA webpages on the BU Research Blog in light of feedback from research staff regarding content, usability, etc. To regularly promote these pages and to track engagement. | Target date: Ongoing Success measures: Improved engagement with the website, as evidenced by CROS19, with at least 50% engaged and finding content valuable. RDS continues to work closely with the RSA to promote activity and consider enhanced routes to engage the RSA members. | University Research Staff Reps | Chris Stantis and Michelle Heward | This is an ongoing task supported by RDS, although engagement in the website has not been monitored. There are plans for this to be managed and monitored by the Research Staff Association going forwards. Success measure not captured in CROS. See ECI1 in new action tracker.
B.2.1f | To work with the Faculties to ensure all research staff have access to allocated funding for external staff development. | Completed This action will continue to be monitored via internal reporting of staff development expenditure. | RDS, OD and Faculties | Julie Northam | In all faculties, research staff have exactly the same access as academic staff to funding for external staff development. This is clear in the policy and guidance documentation issued to research staff in the Faculties.
B.2.3a | To continue to build the sub-principle of performance management into the leadership programmes. | Target date: End 2019 Success measures: A combined Leadership Programme (Academic and PSS staff) to take place in Spring 2019. Launch of a toolkit of models and activities to support the identification of talent and potential, managing performance and succession planning - Spring 2019. Further actions are forthcoming, dependent on BU2025 implementation. These will be added to this action plan in due course. | OD | Chloe Scholey/Sarah Cronin | HoDs/DHoDs programme has now finished (last session 14/09/20) Management Essentials programme put on hold and some sessions starting again in the new academic year. See EI4 in new action tracker.
B.2.3b | To improve promotion of the leadership development programmes, for example, by proactively targeting appropriate research leaders and managers and encouraging them to participate. | Target date: 2021, aligned with BU's Athena SWAN action plan Success measures: Aligned with Athena SWAN, with specific measures to evidence the enhancement of promotion opportunities and increase the number of women in senior academic roles. OD and RDS will continue to promote events and resources, by all suitable means available. BU's Heads of Department are pivotal in the success of this action and will be activity encouraged to engage. | OD and RDS | Chloe Scholey/Sarah Cronin | Progress on this has slowed owing to the COVID-19, however, relevant opportunities are profiled directly to HoDs/other research leaders for promotion and development and is ongoing.
B.2.3d | To explore how best to ensure managers of research staff fully understand, and are able to undertake, the role. To ensure a better consistency of approach to the management of research staff. | Target date: Summer 2020 Success measures: Session delivery with 50% of relevant staff attendance, with at least 75% reporting that the session is good or above OD Adviser/an HR Adviser/RDS to arrange a co-facilitated Supporting Induction & Probation session, targeted at managers of research staff Use of PPDP/Appraisal Brightspace resources by managers of research staff The approach and ownership is currently under discussion between relevant parties. | HR, OD, RDS and Faculties | Chloe Scholey/Sarah Cronin | This action was paused further to the outbreak of COVID-19 and the restructure of HR/OD. Management Essentials were offered to all HoDs and DHoDs throughout 2019 and 2020 as part of the a leadership development programme that took place during 2019 and 2020. See EI5 in new action tracker.
B.2.4a | To continue to operate the BU Bridging Fund Scheme, making improvements where appropriate. | Target date: Revise and implement the updated scheme by spring 2019. Review the scheme annually (each September) and complete an equality impact analysis (each August). Success measures: Increased retention of research staff between contracts/grants as, at present, the majority of those funded through the scheme leave BU after the bridging period. Also, aim to see an increase in the proportion of eligible female researchers who apply to the scheme. There will be an increasing level of promotion of this scheme to both research staff and their line managers with an additional aim of addressing the gender imbalance. We will ensure Executive Deans and Heads of Dept are informed about bridging fund awards and will ensure researchers and their managers are contacted c.6 months before the end of the FTC to invite them to apply for bridging funding. | RDS, HR and Faculties | Emily Cieciura (Julie Northam) | The BU Bridging Fund Scheme is still in operation, and in this last reporting period has been used 15 times, ensuring continuity of employment for research staff. It is reviewed annually (last update is in May 2020) which resulted in changes being made to the scheme in terms of eligibility and the funding models. In 19/20, four staff in receipt of bridging funds were retained at BU, one of whom progressed to a Lecturer position. The scheme is promoted at least twice per year. Equality analysis of the scheme in 2019, with the limited data available, it can be said that the scheme itself does not appear to discriminate unlawfully. The guidelines state that those on parental leave are included within the scheme’s remit. Application rates from male and female researchers are now more even (ratio of 1 to 0.75 male to female applications between 2017-19, compared to 1 to 0.2 male to female applications between 2015-17) and the approval rates indicate female researchers are slightly more likely to receive bridging funding than male research staff (approval rates of 100% for women and 88% for men). Data on ethnicity and disability was available for the first time in the 2019 equality analysis. Approval rates indicate staff with a disclosed disability are slightly more likely to receive bridging funding than those with no disclosed disability (approval rates of 100% for staff with a disclosed disability and 92% for those with no disclosed disability), although the numbers of staff applying for funding who have disclosed a disability are small (2 applications). In terms of ethnicity, there was no difference in approval rates based on disclosed ethnic background (100% approval rates for all applicants who had disclosed this information). The application form does not ask for information on protected characteristics such as age, disability or race/ethnicity which means this information is not readily available to the decision-makers. HR now proactively contact research staff and managers at least six months before the end of a fixed term contract. See EI6 in new action tracker.
B.2.4b | To improve workforce planning and information to Faculties for the proactive management of succession planning and redeployment for research staff. This would support talent retention and career security. This links to Action A.1.0c. | Target date: December 2020 (aligned with Athena SWAN action plan) Success measures: 100% of senior academics leaders to have participated in the forthcoming Talent, Performance and Succession Programme (launching 2019) Within the RCSG context, this action is currently under review with the updated action to focus on talent and succession planning, with 'workforce planning' now a business as usual function | RDS, HR, OD and Faculties | Elaine Sheridan | In September a new MI suite for Faculties and Services was launched. WFP discussions underway including talent management and succession planning. In collaboration with TU's we are now working to some principles on the FTC process that seeks to engage the employee and manager earlier in the process and to plan forward and seek to mitigate end of FTC. FTC's have been reviewed and a number made established - close review and scrutiny to continue. Talent, Performance and Succession planning and developed was embedded within the development programmes for both academic and professional staff that took place between 2019 and 2020. These development programmes were offered to both academic and professional support staff leaders. See EI6 in new action tracker.
B.2.6a | Review promotion and development opportunities for research staff (The RCSG will have the opportunity to feed into this review. Once ratified, development opportunities (including promotional opportunities) will be reviewed, refreshed and aligned to the Framework/Fusion to assist staff in progressing their careers.) | Target date: TBC - This is an identified work stream under BU2025 which needs to be scoped and timeline agreed. Success measures: Implementation of a career framework | RDS, HR, OD and Faculties | Elaine Sheridan | The implementation of a career framework was postponed owing to COVID-19 and the reprioritisation that was required with respect to HR services. However, promotion and development opportunities have been provided through direct university investment into areas of strategic growth (i.e. 1 established PDRA in FST and 2 clinical fellows). Furthermore, the career development of research staff has been enabled through the creation of the Academic Targeted Research Scheme (ATRS). This provides a Senior Lectureship, focused on research for two years at a Grade 8. One of BU's PDRAs as transitioned into this scheme, with a further 5 external candidates securing this development opportunity. See EI3 in new action tracker.
B.2.6c | To produce and promote case studies on how academic and research staff have developed their careers using the RKEDF. | Target date: Ongoing, with monitoring per each academic year Success measures: Aim for annual case studies of two per faculty and across different career stages RDS will continue to seek out the narrative, proactively. Given that the pilot for the learning logs was not sufficiently subscribed to continue as a mechanism for capturing this narrative, these actions will based on focus groups, the annual RKEDF survey and other means to locate and develop suitable case studies. | RDS | Jo Garrad (Emily Cieciura) | This development of case studies has been delayed owing to the retirement of a member of staff, but there are plans in place to generate them as part of future activities. Two case studies have been produced in 2021 in addition to existing case studies, for example: http://blogs.bournemouth.ac.uk/research/researcher-toolbox/researcher-development/careers-guidance-for-research-staff/planning-a-career-in-a-university-in-academia/case-study-dr-zoe-sheppard/ See PCDI3 in new action tracker.
C.3.2a | To review and strengthen the implementation of the new RKEDF (linked to the BU ACF and the Vitae RDF). To continue to involve research and academic staff in the delivery of some of the training sessions for staff and PGRs. | Target date: Summer 2019 and annually thereafter Success measures: Ensure that, wherever possible, BU academics are involved in delivery Based on sources to include BU Staff Profiles, knowledge of staff expertise (such as being external panel members) and RKEDF attendance records, RDS will continue to encourage research staff participation, with a view to inviting them to present to their peers. This will include inviting Acorn Award holders to present at further BU events (for example, all Acord Award holders in 2018 delivered reviews of their internally funded research to the ECRN network and ECRs are providing sessional input within the ECRN 18/19 calendar of events). | RDS and OD | Emily Cieciura (Jo Garrad) | Since 2019 over 100 ECR training sessions have taken place via the RKEDF. Sadly, in this academic year, there has been a reduction in training provision due to covid, late budget finalisation and the loss of the RKEDF facilitator. That said, the RKEDF has supported the career development of research staff and ECRs through the delivery of a range of training sessions focussed on the research sector, processes, specific funders, research skills, research methods, ethics, impact and public engagement. The end of year review, whilst identifying areas for improvement also showed from comments that research staff in the ECRN felt supported by BU both in themselves and their research. RDS have involved academic staff in leading some activities. Examples are Ann Hemingway and Sam Goodman leading the ECR Network; and Richard Berger and Dinusha Mendis participating in delivery of sessions under the Research Council Development Scheme.
C.3.3d | To introduce more robust processes for monitoring staff/PGRs undertaking public engagement activities. To increase the proportion of research staff and PGRs who undertake public engagement. | Target date: Mid to late 2019 and then ongoing Success measures: Depends on mechanism employed, with action plan to be updated when agreed During 2018/19, the Doctoral College will work with the new Engagement Officer (anticipated to commence employment within RDS in January 2019) to develop a number of mechanisms for increasing the number of PGRs undertaking public engagement activities, including promoting the importance of public engagement to PGRs and supervisors, providing sessions on how to engage with the public successfully, finding mechanisms for recording what activity is undertaken. This includes considering use of the HEBCI survey, case studies and, potentially, an internal survey, via the Doctoral College and the RSA, to explore and promote public engagement by research staff and PGRs. The new Engagement Officer, in consultation with the RDS Impact Officers (all four appointed in 2018) will develop strategies to monitor feedback from public engagement and impact activities. | RDS, Doctoral College & RCSG member | Fiona Knight and Genna del Rosa | Training: • The training provision for public engagement with research (PER) has included four sessions with the National Co-ordinating Centre for Public Engagement (NCCPE) as part of the RKEDF, including one on online engagement in response to COVID-19 restrictions. PhD supervisors and ECRs were among those invited to attend the sessions. • The planned training for the RDP in 2019/20 was postponed, though training resources were provided in lieu of the planned session. The session has been reconfigured for March 2021, to include a pre-recorded session and online Q&A. • RDS are currently producing a recorded introductory session to PER, to be shared on Brightspace and promoted to PGRs, PhD supervisors and ECRs. PER opportunities: • RDS have supported PGRs and ECRs to carry out PER both face-to face and online during COVID-19. For example, since 2019, three PGRs and four ECRs have successfully presented at Café Scientifique events. • An ECR was also supported to run an online screening of an original research film in July 2020, followed by a cross-disciplinary discussion involving artists and community partners, reflected upon in a blog post. • RDS has established an internal PER network to encourage collaboration and share best practice. The network currently has 151 members, including ECRs and PGRs. Two meetings have been held so far, one carried out virtually during COVID-19, with more planned. • The ESRC Festival of Social Science 2020 was successfully held entirely online, including one event proposed and led by a PGR, two events with PGRs as collaborative leaders, another led by an ECR and further events involving ECRs as part of the research teams. • Funding awarded by the Research Impact Panel has included PER projects led by ECRs, delivered with support from RDS. Celebrating PER: • RDS has included PGR case studies in their work raising the profile of PER, for example by sharing the PER experiences of PGR speakers at Café Scientifique events on the Research Blog. RDS has also obtained detailed feedback from PGRs involved in ESRC Festival of Social Science events, with a view to creating case studies in several forms. • Due to the COVID-19, the development of annual prize ceremony, possibly as part of the Annual Conference, was put on hold. However, the DC will consider a PE prize when working on the development of an annual PGR prize ceremony going forward. Reporting: • The HE-BCI Table 5 data collection process has been improved by RDS to collect more data from academics, including details of PGR involvement in PER activity across BU. • RDS has launched a survey for academics to complete post-PER activity, which notes career stage (PGR, ECR, etc.) and measures the impact of PER on academics. • No new studentship applications were held this year however, the DC will develop a process going forward to identifying PE listed as part of the studentship application, recommending PE training via the RDP and following up on outcomes. • The DC continues to work with IT to identify a replacement for ResearchPAD and will continue to investigate adding a mechanism for capturing and reporting on PE involvement within the new system.
C.3.3e | To hold a public engagement event as part of the Festival of Learning for researchers to present their work. | Target date: Summer 2020 Success measures: Event delivered by the RSA The RSA plans to engage with the Festival of Learning, subject to event requirements. These will, potentially, be in collaboration with the ECR Network. | University Research Staff Reps | Chris Stantis and Michelle Heward | It was not possible to hold a Festival of Learning in 2020 or 2021 (COVID-19), but other opportunities have been made available. Cafe Scientifique offers researchers the opportunity for real public engagement, with monthly events including Dr Emma Portch sharing research in Oct 2019 on how psychologists can work with the police to improve the quality of facial composites, and Dr Ediz Akçay discussing how companies use AI and voice recognition to track their users. We also co-ordinated ten events as part of the ESRC Festival of Social Science in 2019, with academics sharing their research with a variety of audiences, including Dr Elvira Bolat discussing the power of social media influencers, and an interactive installation from Dr Emma Kavanagh and Dr Adi Adams on violence in sport coaching.
C.3.6c | To develop better support for local induction of academic and research staff. | Target date: December 2020 Success measures: Improved induction experience for new starters with, aligned to Athena SWAN, the aim for at least 80% of women to be satisfied with each element of their induction experience. The current process is currently under review within OD and RDS. The aim is to link this action with other initiatives within BU to ensure that these central processes support and encourage local processes. Processes will be reviewed and updated in line with the approval of the 'Induction and Mandatory Development' paper at ULT in October 2018 and the launch of the new Core Programme in 19/20. | OD | Chloe Scholey/Sarah Cronin | Induction toolkits pending final sign-off (linked with broader project to update OD staff intranet resources). These as well as the revised intranet resources are aimed at supporting the induction experience of all staff at both a corporate and local level. Researchers experience of this will be evaluated through the annual survey conducted by RDS. HR/OD closely monitoring attendance at induction events. More Welcome to BU events were scheduled throughout lockdown and these were run virtually. RDS run regular induction events aimed specifically at introducing BU policies and procedures and the RDS team to the new members of staff. Since 2019, 15% of BU's new research staff have attended - 60% male, 40% female. This is an increase on previous years. One attendee this year said of it "It's a helpful session, especially if you're new." On a monthly basis, RDS receive details of research staff who have joined BU. A welcome email with a plethora of useful information is despatched to each new member of staff and their line manager. They are also put in touch with their RSA reps.
C.3.7 | To develop and implement documentation on research staff career pathways. (Externally facing opportunities to differentiate this action from that of A.1.2a) | Target date: TBC - This is an identified work stream under BU2025 which needs to be scoped and timeline agreed. Success measures: Implementation of a career framework | HR | Elaine Sheridan | Research staff career pathways have been on hold due to COVID-19. However we do now have standardised job descriptions for research staff.
C.3.8a | Develop the BU Mentor Network | Target date: Spring/Summer 2019 Success measures: A pilot is underway within two of the four BU faculties, with success measures to be agreed as part of the pilot. RDS and OD are in discussion regarding using the ECR Network as a pilot using SUMAC to allocate mentors. There are also local schemes within faculties which need to be drawn into this planned BU-wide initiative. Within the BU2025 context, action 66 states that we will strengthen leadership across BU by repositioning current and future leaders, including the Professoriate, to act as leaders consistently, including via coaching and mentoring, building teams around them and succession planning | OD and RDS with Faculty consultation | Chloe Scholey/Sarah Cronin | HR/OD continuing to support Faculties in establishing SUMAC schemes to facilitate local mentoring matches, tracking of mentoring relationships etc. All Faculties introduced Faculty-based mentoring schemes in autumn 2019 and all research/academic staff should now have a mentor, which is an action in BU2025.
C.3.9a | To continue to monitor engagement with appraisal ensuring that research staff have annual appraisals and personal and professional development plans in place. To ensure that Core is being updated accurately with information on completed appraisals for research staff. To clarify the requirement for objectives to be set for research staff as part of the probationary period and to build this into the induction and probation workshops for the line managers of research staff. | Target date: October 2019 Success measures: 100% of research staff to be having appraisals that are also logged on CoreHR (iTrent) With the issue of accurate logging of appraisal activity being highlighted, OD plans to raise awareness of the need to record appraisal activity and provide greater information of what constitutes a 'good appraisal' . Importantly, this in within the changing context for appraisals, where the process is under review at a BU-wide level. Depending on the outcome of this, there will be a greater requirement for stakeholder buy-in to new processes and the appraisal ethos. This action is subject to change, as the approach to PPDP and appraisal is currently under review, with this action to be updated accordingly. | OD and Faculties | Chloe Scholey/Sarah Cronin | There is no facility to log appraisal data in the new HR system, iTrent and Faculties are now expected to log these locally. However, CROS19 suggested that just 32% of researchers had received an appraisal action, and as such this will be addressed in future (see PCDM1).
C.3.9c | To review the Code of Practice for the Employment and Development of Research Staff and procedural guidance on probation, appraisal and pay progression for research staff to ensure it is clear to follow and consistently applied across all Faculties. | Target date: CoP to be reviewed annually or more often, if required Success measures: Updated CoP Within this, there is a review of probation procedures which has been delayed to align to BU2025 activity. This is an identified work stream under BU2025 which needs to be scoped and a timeline agreed, in addition to identifying a suitable person to lead. This review may lead to changes in the CoP. | RDS, HR and OD | Emily Ciecura & Elaine Sheridan | The Code of Practice was updated, released and publicised in January 2020 and is now reviewed annually. The research staff reps are involved in the reviews.
C.3.9d | To successfully deliver the RKEDF. To monitor research staff engagement with the programme. RDS and OD to ensure that staff understand how the pathways within the framework can support their achievement of outputs identified in the Academic Career Matrix as well as how it aligns to the Vitae RDF. To promote and communicate the programme across the university. | Target date: Ongoing - reporting to faculties and relevant BU committees biannually Success measures: Based on BU2025 KPIs - predominantly meeting internal research bidding and income targets, along with attendee feedback being 75% good or above BU's research staff are to be specifically monitored within the reporting matrix for the RKEDF, allowing groupings of research staff accessing the RKEDF to be monitored and reported to faculties, to ensure equitable access to opportunities, where access requires approval from their Head of Department. In addition, dialogue will continue with the RSA in this regard. | RDS and OD | Emily Cieciura (Jo Garrad) | RDS delivers a large range of training activities under the RKEDF. Attendance is monitored and feedback collated showing that, of those who responded, overall satisfaction ranged from good to excellent. This information is used to evaluate the RKEDF and is reported to RPMC annually with recommendations for improvement. However, due to financial restrictions, the RKEDF has been significantly reduced during 2019/20 and for 20/21, although plans are in plan to accelerate the framework in 21/22 as part of C19 recovery. A session was run to ensure that staff understand how the pathways within the framework can support their achievement of outputs identified in the Academic Career Matrix as well as how it aligns to the Vitae RDF. We have situation statements to guide academics to the type of RKEDF activities they may be interested in, e.g. 'I am new to research'. We carry out university wide advertising for the training programme. A brochure is produced in September, and intranet pages are updated. We use the BU research blog, faculty blogs, the ECR network, RSAs, HoDs and DDRPPs to advertise what's coming up, and to advertise specific events. The RSA and ECR Network are particularly useful in making research staff aware of development opportunities. See PCD13 on new action tracker
C.4.11 | To review the content and delivery of the development schemes on a regular basis. | Target date: Ongoing Success measures: Aim for at least 75% of attendees to have found each event good or above; awareness of provision to be enhanced Through the RKEDF and ECRN, the RSA will be promoted, with an increased targeting of those staff transitioning to the next stage in their career (from PGR to post-doc to the first established post) with reference to staff retention and succession. This will require working across BU functions to include, HR, Organisational Development, the Doctoral College, the Careers Service and RDS. From the meeting on 27/4/18, research staff requested support with funding applications - access to examples of applications and the opportunity to talk to previous applicants at BU. Both these provisions are already in existence, through the RDS Bid Library and records of applications. For this action plan, promotion to research staff will be improved as a lack of awareness has been identified. | RDS and OD | Emily Cieciura (Jo Garrad) | The contents have been reviewed regularly, particularly using survey outcomes. Changes were made as a result of outcome from the 2019 CROS and PIRLS survey. A planning cycle took place in May 2020 to ensure the content of the reduced RKEDF would meet the needs of academics where Faculty Executive were consulted. Surveys of attendees of training events have shown that of those who responded, the rate of satisfaction with the training was good to excellent. A further internal survey was conducted to inform future training and development schemes. Research staff are encouraged to respond with their feedback via the RSA and the ECR Network. For example, feedback from the RSA about the Academic Researcher Induction has informed recent changes in approach. Recently, all faculties have confirmed that research staff have equal access to research funding and support for funding applications. See PCD13 on new action tracker
C.4.13c | To clarify the role and responsibilities for the University and Faculty Research Staff Reps. To ensure research staff know about the reps and understand how to raise matters for discussion at RPMC, RCSG and URPPC. | Target date: April 2019 and then meeting no less than once annually Success measures: All faculties will have at least one RSA Rep and there will be two University reps in post The current recruitment round was commenced in November 2018. Once all post holders are in place, there will be a meeting with all representatives, hosted by RDS, to communicate policies and procedures. This will then be repeated annually, or as required by the changing membership of this group. The RSA Guide will be made available as soon as practicable. | RDS and Research Staff Reps | Emily Cieciura | The Research Staff Association has a Terms of Reference and the roles of University Rep and Faculty Rep have role descriptions. All the faculties are represented by at least one representative. The reps are also invited to the RCSG, and to the quarterly Faculty Research and Professional Practice Committee meetings as attendees. The RCSG reports to and the University RSA reps attend the URPPC meetings. RDS have facilitated regular RSA meetings, and provide updated lists of research staff to the faculty reps so they can establish contact and represent their interests and concerns. See EC12 on new action tracker
D.5.1a | To continue to embed the principles of the Concordat to Support Research Integrity and to raise awareness of its importance. | Target date: Summer 2019 (CROS data) Success measures: CROS19 data to show an increase from 17% to 85% for the proportion of research staff who have heard of the Concordat. Subscription to UKRIO (2019), with exploration of the training opportunities offered as part of this. See Integrity toolkit (http://ukrio.org/wp-content/uploads/UKRIO-Royal-Society-Integrity-in-Practice.pdf). A gap analysis has been undertaken, which highlighted the lack of information known on activities undertaken within Faculties to support students. The Analysis highlighted a gap between policy and operational activates (staff and student levels). Action to work with URPPC to secure buy-in and to agree to embed Integrity as part of the mentoring process. The Code of Good Research Practice has been updated to strengthen research integrity (updated Oct 2018 and January 2019). The analysis highlighted the need for a Research Integrity Framework (pulling together research integrity policies) with is this to be actioned in 2019. Embedded into all ethics based training session run by RDS (ongoing). Investigate Epigeum e-learning modules (2019): Research Integrity: Concise (Published April 2016) Research Integrity: (Published July 2012). | RDS and Ethics Chairs | Paul Lynch | The Concordat itself was updated in October 2019 following consultation. The BU webpages were updated and given a makeover which foregrounds the concordat and governance more broadly (2020) , see https://www.bournemouth.ac.uk/research/research-environment/research-governance-integrity/ Subscription to UKRIO has not yet happened due to budgetary restraint, as the cost of a training video subscription is removed going forward we would hope to subscribe to UKRIO. The CROS19 survey was reported to URPPC in January 2020. Those respondents knowing of the Concordat rose from 26% to 33% for BU (from 2017 to 2019) and the national figure for 2019 was 37%. The CROS and PIRLS surveys have been replaced by CEDAR following consultation - the consultation was promoted on the blog. A questionnaire is being circulated to programme teams by the Governance Adviser in semester 1 (2020/21) to gather information on the training they received to assist in improving support for students. The Code of Practice has been further updated in relation to integrity in 2020 and this is going through approval. Integrity has been added to staff and PGR inductions and introductory emails. BU signed the new concordat in November 2020. Owing to COVID, this was celebrated at online events run for the Research Staff Association (reaching 100% of the group) and the Early Career Research Network (11% of the group) - a combined total attendance of 27 members of staff.
D.5.1b | To produce an annual statement outlining our activities in supporting the Concordat to Support Research Integrity and presented to URPPCs for approval; this will be shared with research and academic staff. | Target date: Annually, with the next report due in October 2019 with URPPC to ratify this report Success measures: Annual review built into existing processes To be compliant with the Concordat to Support Research Integrity an annual statement must be made publicly available (https://blogs.bournemouth.ac.uk/research/researcher-toolbox/the-concordat-to-support-research-integrity/). The latest report was ratified by URPPC in Oct 2018 | RDS | Paul Lynch | The BU Research Integrity statement is published annually after approval from URPPC. Previous statements are published here: https://www.bournemouth.ac.uk/research/research-environment/research-concordat/concordat-support-research-integrity) See ECI5 on new action tracker.
D.5.2a | To finalise the updated commercialisation and IP policy. | Target date: Summer 2019 Success measures: Finalised IP policy plus an agreed plan for strengthening IP/commercialisation support to be in place (BU2025 action). | OVC | Julie Northam | The Research Commercialisation Manager (RDS) is now providing one to one support for researchers where required - as of April 2020, now typically supporting 4-5 enquiries per week from researchers. This is a step change in support for researchers - where previously there was no central support available to explore IP queries and commercialisation routes. The new IP policy has been approved (formally by BU's Board in April 2020) and a set processes and appropriate governance (through a central committee) has been implemented. This has enabled, for example, a researcher to deliver a medical device which is now in use in the NHS.
D.5.3a | To continue to review, enhance and embed the ethics governance structure, including raising awareness of the importance of research ethics across the University. As part of the new Academic Career Framework, to deliver additional sessions targeting specific areas of interest (working with children, informed consent under the Mental Health Capacity Act, etc.) to engage staff around ethical issues pertinent to their own subject areas and research interests. | Target date: May 2019 for ratification with workshops to be delivered in 19/20 Success measures: 0% ethical complaints Working with UREC and Panel members to provide a suite of workshops targeted at research governance (to include ethics/clinical governance, data management) which will fit with the RKEDF. (2019) BU currently subscribe to Epigeum's Ethics 1 & Ethics 2. A paper will be submitted to UREC in May 2019 for ratification and implementation. | RDS and Ethics Chairs | Paul Lynch | BU promotes an understanding of responsible conduct through our culture, policies, current training, and research activities. An enhanced programme of training opportunities has been discussed at the Research Ethics Committee and further meetings have since taken place with the Research Ethics Panel Chairs and RDS Governance Team.
D.5.5a | To regularly review provision to ensure it meets with researcher and research manager needs. To use CROS, PIRLS and staff surveys as a means of collating this information. | Target date: Summer 2019 (CROS19 and PIRLS) Success measures: Evidence within the support and career development sections of CROS19 and PIRLS19, showing percentages maintained or improved With reference to GEN1 and relevant RKEDF actions, such provision is monitored and evaluated as part of standard reporting to relevant committees and senior management. In addition, there is regular consultation with faculties, via Deputy Deans for Research and Professional Practice (DDRPPs) and Heads of Department. Through the year, there is an annual RKEDF survey, feedback requested after each event in the programme and via cross-departmental focus groups, which include non-faculty staff with researcher development interests. In 2019, this will be supplemented by the responses to the CROS and PIRLS surveys. | RCSG (all) | Emily Cieciura | We aimed to at least maintain the proportion of research and academic staff engaging with development opportunities, as measured through CROS and PIRLS. Overall the proportion seems to have decreased slightly for research staff and increased slightly for academic staff: - 44% engaged with the RKEDF (CROS19) compared to 60% (CROS17) - 11% engaged with BU leadership programmes (CROS19) compared to 7% (CROS17) - 24% engaged with the Writing Academy (CROS19) compared to 33% (CROS17) - 61% engaged with the RKEDF (PIRLS19) compared to 49% (PIRLS17) - 45% engaged with BU leadership programmes (PIRLS19) compared to 51% (PIRLS17) - 40% engaged with the Writing Academy (PIRLS19) compared to 38% (PIRLS17) Actions based on 2019 CROS and PIRLS findings were incorporated into the action plan. A planning cycle took place in May 2020 to ensure the content of the reduced RKEDF would continue to meet the needs of academics, where the Faculty Executive were consulted. This has been used inform our future action plan in line with the new Concordat (PCDM4).
D.5.5b | To deliver training to research leaders, line managers and mentors on how to provide careers advice to academic and research staff, ideally built into the RKE Development Framework. | Target date: Summer 2020 Success measures: PIRLS19 to show an increase in the number of respondents who feel confident in providing advice on careers inside HE (75%) and outside HE (50%) This provision is currently in development with the next meeting scheduled for 28/01/19. This will include consideration of enhanced provision before the next Vitae meeting at BU planned for 2020 (see action GEN1). | RDS and OD | HR | Whilst this has not been directly incorporated into the RKEDF, careers advice and extensive services are available to all postgraduate researchers, research staff and academic staff. PIRLS19 data unfortunately showed a slight decrease in the confidence of staff to provide careers guidance inside HE (56%) and outside of HE (44%).
D.5.5c | To produce a simple A-Z document for research staff signposting them to development opportunities available. This will be provided to new staff and their line managers with other induction materials. | Completed OD to keep this resource updated. | OD | Chloe Scholey/Sarah Cronin | This action has been completed and the resource continues to be maintained. Research staff reps were involved in the development of the guide. It is sent to all new research staff when they join BU.
E.6.1 | To annually review equality, dignity and diversity at BU. | Target date: February 2019 Success measures: Report is approved and published with the planned programme of work for the following year is undertaken with at least 80% to agree that BU is committed to this agenda (CROS19 / PIRLS19) | Equality and Diversity Steering Group | James Palfreman-Kay | The report is produced annually, presented to BU committees, and there is an annual programme of work. One highlight was the department for Archaeology and Anthropology being the fourth department to be successfully awarded. The University has considered the recommendations of the Equality and Human Rights Commission report on Racial Harassment in Higher Education. A review of the BU position against the findings has been undertaken and next steps are being worked through.
E.6.3a | All departments to achieve at least bronze by 2025, under the expanded criteria of the new Athena SWAN charter, with the aim of achieving an institutional silver award in 2022 | Target date: 2025, with interim target of three departments per year, all achieving at least bronze recognition Success measures: BU2025 KPI is for all departments to achieve at least bronze by 2025 BU2025 and the national review of Athena SWAN may result in amendments to this action. Currently, the aim is for all Departments to obtain at least bronze by 2025. | Athena SWAN SAT | James Palfreman-Kay | Three departments have achieved the Athena bronze award: Media Production, Psychology, Life & Environmental Sciences and Archaeology & Anthropology. The Department of Design & Engineering are submitting in May 2021. There is a University Leadership Team approved schedule for departmental submissions and all departments have appoints Departmental Athena Swan Leaders.
E.6.3b | To make an institutional submission for a bronze Race Equality Charter award. | Target date: July 2019 for submission, 2021 for action plan Success measures: Submission to the Race Equality Charter with the aim of securing their Bronze Award, followed by adherence to the submitted action plan | Race Equality Charter SAT | Geli Roushan | Delayed by Covid, submission is planned for summer 2021.
E.6.4 | To review family leave policies. | Completed Although noted as complete, this action will require further consideration following the outcome of the Athena SWAN submission in November 2018 and the action plan will be updated accordingly. | HR | Elaine Sheridan | Completed.
E.6.9 | To evaluate the Dignity and Respect Policy and Procedures. | Target date: Ongoing Success measures: CROS19 evidencing increased engagement to 50% The Respect at BU video, which is updated annually, is being promoted to target groups across BU. Please see https://youtu.be/C-LkzU31L3U. Work will continue with regard to the Hate Crime project. We will increase the number of research staff engaging with equality and diversity training from 29% in CROS17 to 50% by CROS19. | Equality and Diversity Adviser | James Palfreman-Kay | The Dignity and Respect policy and procedures have been reviewed. In addition, Respect at BU work videos have been produced for staff and students. See https://www.youtube.com/playlist?list=PLCAGWsnZKYKXKOQDkwsnpfor3EyQnnsCa Respect at BU sessions have been delivered at BU. The hate crime project has completed and BU has maintained its membership of Prejudice Free Dorset. The aim of this network is to challenge prejudice in Dorset so that all individuals can go about their daily lives safely and with confidence. E&D training remained at 29% (CROS19)
F.7.1a | To review the membership, role and purpose of RCSG, as well as progress with the action plan, on a regular basis. | Target date: Summer 2019 then annually thereafter Success measures: The RCSG will have stability in terms of this action which will be fit for purpose to the end of this plan period At the meeting on 28/11/18, the role and membership review was commenced with review planned to be completed by mid 2019. | RCSG (all) | Emily Cieciura (Julie Northam) | Membership has been reviewed, with posts recruited to and ToRs updated. The action tracker has continued to be reviewed quarterly by the group, with inputs provided and updated. Meetings have taken place at a minimum quarterly. Further to the signature on the new concordat, the RSCG will now be Co-Chaired by a DDRPP and Senior RDS Manager, and discussed at quarterly meetings between the RDS executive and all DRRPPs.
F.7.1b | To provide updates to Deans via ULT. These briefings will provide a summary of key points they need to know and over which they have influence. | Target date: February 2019 and then annually Success measures: Production and circulation of briefings at least annually A briefing note is to be produced as part of 6 year review, with future briefings to be made available according to a schedule to be agreed with the RCSG, with a briefing produced at least annually. | RCSG | Emily Cieciura (Julie Northam) | Briefings to Faculty leadership team has been provided through URPPC and quarterly meetings with the DDRPPs. An annual reported is provided to URPPC to update on the Concordat.
F.7.1d | To increase the proportion of academic/research staff who feel integrated into their Faculty, University and disciplinary communities. | Target date: Summer 2019 (CROS19) Success measures: CROS19 to show all categories above 75%, with reference to CROS17 below CROS 2017: Agree / strongly agree they feel integrated into: - dept research community - 69% (63% 2015) (76% nationally) - dept community - 50% (75% 2015) (67% nationally) - BU research community - 75% (38% 2015) (57% nationally) - wider disc community - 81% (75% 2015) (65% nationally) | RDS, RCSG and Faculties | Emily Cieciura (Julie Northam) | The majority of BU respondents felt integrated into the research communities in their department, wider discipline(s) and at BU, however, only 62% felt integrated into their wider departmental communities. At an institutional level, less than half (45.9%, 54% nationally) agreed they were integrated into BU’s research community, significantly down from 75% in 2017. Only 48.6% agreed that they felt integrated into their wider disciplinary community (63% nationally). This is a notable decrease, at BU, from 81% in 2017 and 75% in 2015 (CROS19).
F.7.2b | To run CROS and PIRLS in spring 2019. | Target date: As per CROS and PIRLS survey release dates Success measures: Response rates - CROS 35% and PIRLS 40% The CROS and PIRLS surveys are planned to run in 2019, with RDS taking the lead in promotion. 2017 response rates: CROS - 29% (16 responses out of a target population of 56); target was 30%. PIRLS - 29% (62 responses out of a target population of 215); target was 40%. | RDS, RCSG and DDRPPs | Emily Cieciura (Julie Northam) | We have carried out CROS and PIRLS surveys to date, and acted on the results provided. In 2019, response rates had increased to 57% (37 responses out of a target population of 65). PIRLS had a response rate of 38% (101 responses out of a target population of 266).
F.7.3 | To continue to monitor the expectations of signatory funders in relation to the implementation of the Concordat. | Target date: Ongoing Success measures: Review dependent, with action plan to be updated in response to consultation outcome This ongoing action is being managed by RDS and awaits the result of the consultation into the review of The Concordat, with recommendation 13 (a revised Concordat should include a new Principle for funders. Funders should ensure that the Principles of the Concordat are adopted through changes to funding processes) being of particular note and driving the response to this action in the period to 2021. | RDS | Emily Cieciura (Jo Garrad) | The expectations of signatory funders is monitored on an ongoing basis. Each change is reviewed and communicated to RDS. BU signed the revised Concordat in November 2020. The RCSG will now be Co-Chaired by a Deputy Dean for Research & Professional Practice with the Senior Research Development & Support Manager.
F.7.4 | To continue to engage with Vitae and colleagues at other universities to share good practice internally and externally. | Target date: September 2019 and on-going Success measures: This will differ depending on the action From the DC perspective, for PGRs, we will continue to engage with VITAE and identify and introduce best practice from other HEIs, aim to influence the sector by presentations at relevant conferences, and showcase evidence of benefits of our programme to the PGR community. We will aim to engage the ECR community as facilitators on the PG RDP programme to both enhance their development opportunities and enhance those of the PGRs. Staff in DC, OD and RDS plan to attend the Vitae annual conference and other relevant events to maintain professional awareness and knowledge. | RDS and the Doctoral College | Fiona Knight | The Doctoral College will continue to horizon scan for opportunities to share best practice in the sector. Vitae frameworks are used for the development of training opportunities. We continue to we look at other institutions' HREiRA action plans, etc and engage with the case studies available on the Vitae website, cascading good practice and ideas internally. We also work across informal networks (for example regional Universities) to undertake good practice exchanged to embed good ideas in working practices.

## Acronyms
ACF – Academic Career Framework
ADD - Academic Development and Diversity
ACORN Fund - Acceleration of Research and Networking
ATRS - Academic Targeted Research Scheme
CE Mark - Conformité Européene
CEDARS - Culture, Employment and Development in Academic Research Survey
CoP - Code of Practice
CROS - Careers in Research Online Survey
DDRPP - Deputy Dean for Research & Professional Practice
DHoDs - Deputy Heads of Department
ECR - Early Career Researcher
ECRN - Early Career Researchers Network
EDI - Equality, Diversity, Inclusion
ESRC – Economic and Social Research Council
FRPPC - Faculty Research and Professional Practice Committee
FTC - Fixed Term Contract
FTE - Full-Time Equivalent
FST - Faculty of Science and Technology
HE-BCI - Higher education and Community Interaction
HoDs - Heads of Department
HR - Human Resources
HREiR - HR Excellence in Research Award
HROD - HR and Organisational Development
IMIV - Institute of Medical Imaging & Visualisation
IMSET - Institute for the Modelling of Socio-Environmental Transitions
IP - Intellectual Property
KPI - Key Performance Indicators
MI (suite) – Management Information
OD - Organisational Development
PE - Public Engagement
PER - Public Engagement in Research
PGR - Post Graduate Researcher
PDRA - Post Doctoral Research Assistant
PIRLS - Principal Investigators and Research Leaders Survey
PPDP - Personal Professional Development Plan
RCSG - Research Concordat Steering Group
RDF - Researcher Development Framework
ResearchPAD - Platform where PGRs document supervision
RKEDF - Research & Knowledge Exchange Framework
RA - Research Assistant
RCM - Research Commercialisation Manager
RDS - Research Development & Support
REC - Race Equality Charter
RI - Research Institute
RPMC - Research Performance Management Committee
RSA - Research Staff Association
SIA - Strategic Investment Area
STEAMLab - Science, Technology, Engineering, Arts , Maths Laboratory
SUMAC - Mentoring platform/company
ToRs - Terms of Reference
TU - Trade Union
ULT - University Leadership Team
UREC - University Research Ethics Committee
URPPC - University Research & Professional Practice Committee
VLE - Virtual Learning Environment
WFP – Work Force Planning