## Action tracker
HREiR Action plan template (2021-2023)
Details
| Institution name: | Bournemouth University | The institutional audience* for this action plan includes (complete or delete, as appropriate):
| Cohort number: | 8 | Audience | # | Comments
| Date of submission: | 2021-05-01 | Research staff | 68
|  |  | Postgraduate researchers | 568
|  |  | Research and teaching staff | 660
|  |  | Teaching-only staff | 0
|  |  | Technicians | 15
|  |  | Clinicians | 11
|  |  | Professional support staff | 972
|  |  | Other (please provide numbers and details): | 6 | University Executive Team
| Obligation | Action | Success measure (SMART) | Deadline | Responsibility | Progress update (to be completed for submission) | Outcome/ result | Old Concordat principle and clause
Environment and Culture
Institutions must:
ECI1 | Ensure that all relevant staff are aware of the Concordat | 1a. Create a dedicated hub of information for research staff on how to progress their careers. 1b. Hold two engagement events per year, led by the RSA, promoting the work of researchers and the importance of the RCSG, as well as to obtain feedback to inform future work and actions. 2. RSA, supported by RDS to promote activity and engagement. 3. Ensure the Concordat is a standing agenda item at the FRPPCs and that matters raised are suitably discussed at URPPC. 4. Monitor improved awareness of the Concordat through annual surveys (both CROS and internal). | 1a. 100% of research staff to be advised by RDS every three months of the opportunities available. 1b. Increase attendance at engagement events from c20 individuals to 50% of research only staff and c5% of staff on academic contracts. 2. Improved attendance at RSA events to c50% of staff on research only contracts. 3. All FRPPC/URPPC Agenda/Minutes to reference progress towards the research concordat. Report annually to URPPC compliance of this. 4. Reduce the number of researchers who have never heard of the Concordat from 47% in 2019, to 20% in 2021 (CEDARS). | 2023-07-01 | Senior RDS Manager |  |  | New
ECI2 | Ensure that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers | 1. RCSG to review the policies with relevance to researchers annually and agree input with policy owners annually. 2. Promote policies relevant to research staff on the staff intranet. Link relevant policies within the BU Research Blog area 3. Promote relevant policies in the RDS Academic & Researcher Induction and at twice yearly event 4. Undertake and publish Equality Analysis for any updated or new policies and procedures. | 1. Minute the RCSG review of policies impacting researchers annually in June each year. 2. RSA reps to promote policies in September each year through FRPPC. 3. 100% of new research staff are invited to the RDS Academic & Researcher Induction, 75% to attend and 90% to feedback the session is helpful. 4. 100% of policies relevant to research staff to have an equality analysis that is undertaken and published annually (or as stated on the Policy if not annually). | 2021-07-01 | Senior RDS Manager |  |  | P2.1 P6.8
ECI3 | Promote good mental health and wellbeing through, for example, the effective management of workloads and people, and effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues | 1. Promote good mental health and wellbeing (including how to get support for discrimination, bullying and harassment) through communications to researchers and sessions at events. 2. Link the Health, Safety and Wellbeing team directly to the RSA through an annual event which addresses the specific challenges to researchers and agrees an action plan for the way forward. | 1. Sign posting for good mental health and wellbeing to be included in 100% of communications and at bi-annual engagement events. 2. Action planning event to take place annually with demonstrable progress made against the actions provided year on year. Create an action plan for this and aim for 75% of researchers to be on-track or completed. 3. Record an increase in the proportion of researchers believing that BU promotes better mental health from 68% to 75% in CEDARS. | 2023-07-01 | Head of Heath, Safety & Wellbeing |  |  | P6.9
ECI4 | Ensure that managers of researchers are effectively trained in relation to equality, diversity and including, wellbeing and mental health | 1. Continue to provide wellbeing development and guidance for Managers 2. Provide equality, diversity and bias awareness development for managers 3. RDS to promote wellbeing resources to Managers of researchers | 1. Establish a baseline for the managers of researchers undertaking relevant training. 2. Aim for 100% of mandatory training elements (i.e. unconscious basis training) to be completed by managers of researchers and 50% of non mandatory components. | 2023-07-01 | Equality & Diversity Adviser |  |  | P2.3
ECI5 | Ensure that researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity | 1. Provide training on research integrity through the RKEDF; to include debate on what the term means and why it is essential for practice. 2. RDS to monitor exceptions and facilitate one to one training for researchers where breeches have occurred. 3. Ensure key information (including the Research Integrity Statement) is kept up to date on BU's website. | 1. 100% of research staff to be offered training on research integrity through the RKEDF on an annual basis. 2. 100% researchers deemed to have not maintained the highest standards of research integrity to be offered supported to improve practice 3. 100% of reseachers to be sign posted to the Research Integrity Statement on an annual basis. | 2022-07-01 | Faculty DDRPP |  |  | P6.1
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and use the outcomes to improve institutional practices | 1. Undertake an annual survey of research staff to review the progress of the research concordat in addition to undertaking CEDARS every other year. 2. Twice per year at Research Concordat Engagement events, facilitate tripartite discussion on enabling the research concordat. 3. Develop case studies on the progression of research staff and the role of professional service staff. | 1. Engagement of over 50% of research staff in annual survey. Analysis to be led by RSA representatives and shared through central corporate communications once per year. 2. Twice yearly output of tripartite dialogue to be fed into action planning. 3. Profile two research staff case studies and one professional service staff case study per year. | 2022-07-01 | Senior RDS Manager |  |  | P6.10 P7.5
Funders must:
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | N/A | N/A | N/A | N/A |  |  | P6.6
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers | N/A | N/A | N/A | N/A |  |  | New
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions | N/A | N/A | N/A | N/A |  |  | P6.6
Managers of researchers must:
ECM1 | Undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work | 1. Managers of researchers to undertake training on EDI and implement inclusive working practices in their work 2. See ECI3 | 1. Departmental Athena SWAN submissions/associated action trackers to demonstrate that 90% of managers of research staff have undertaken EDI training and there is demonstrable evidence of inclusive working practices (see an increase in CEDARS data in the number undertaking training up from 63% to 90%; and those reporting the training to be beneficial to increase from 55% to 75%). Increase visibility and awareness of mandatory training and development, ensuring completion of training by new starters 2. 100% of development programmes offered and coordinated by RDS to have embedded E&D principles. | 2022-07-01 | HoDs/line managers of researchers |  |  | New
ECM2 | Ensure that they and their researchers act in accordance with the highest standards of research integrity and professional conduct | 1. Managers of researchers to receive training on research integrity and appropriate professional conduct. 2. Managers of researchers to work with researchers them to ensure they are attending relevant training and maintaining the highest standards of research integrity and professional conduct. | 1. Faculty DDRPPs to confirm that 100% of managers have been offered appropriate training. In CEDARS, 90% (up from 71%) to considered to be very important as an excellent researcher leader. 2. Research Staff Association representatives to feedback twice per year to DDRPPs the extent to which relevant training/embedding of practice is taking place across the researcher community. | 2022-07-01 | HoDs/line managers of researchers |  |  | New
ECM3 | Promote a healthy working environment that supports researchers' wellbeing and mental health, including reporting and addressing incidents of discrimination, bullying and harassment, and poor research integrity | 1. Managers of researchers to promote a healthy working environment. 2. Managers of researchers to ensure that researchers are aware of resources to support their mental health and wellbeing, and also how to report/address incidents of discrimination, bullying and harassment, and poor research integrity. | 1. Research Staff Association representatives to feed back quarterly on the extent to which managers of researchers are promoting a healthy working environment, and to encourage research staff to escalate issues impacting their working environment with their mentors/Faculty DDRPPs/HR & OD Partnership Manager (as appropriate) if they have concerns. Confirmation in RCSG minutes that this is taking place successfully. 2. Faculty DDRPPs to confirm that 100% of managers have received the relevant resources to sign-post their research staff to and willingness to discuss concerns raised by researchers directly with them/another nominate representative of their Faculty executive team. | 2022-07-01 | HoDs/line managers of researchers |  |  | P6.9
ECM4 | Consider fully, in accordance with statutory rights and institutional policies, flexible working requests and other appropriate arrangements to support researchers | 1. Managers of researchers to fully consider and enable flexible working requests to support researchers, wherever possible 2. Managers to highlight existence of flexible working policies and processes and examples of best practice 3. Managers to implement locally the people operating model (which will provide an opportunity for staff to consider more flexible working arrangements) when published | 1. Faculty DDRPPs confirm on a quarterly basis the extent to which that flexible working opportunities are being utilised by their community of researchers (further to feedback at FRPPC meetings) 2. HR to report how many formal flexible working requests have been logged on iTrent annually. | 2022-07-01 | HoDs/line managers of researchers |  |  | New
ECM5 | Engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | 1. DDRPPs to ensure that researchers have the opportunity to feed into developing a positive research culture, e.g. through input into the development of departmental and faculty policies. | 1. At least one example to be identified each year on how researchers have fed into policy development, to published on the central Research Hub. | 2022-07-01 | HoDs/line managers of researchers |  |  | New
Researchers must:
ECR1 | Actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students | 1. Researchers to develop actively engage in opportunities to develop BU's research culture, and for established RSA members to support new appointments (providing formal mentorship where appropriate). | 50% of RSA members to have supported/mentored 1 or more new researchers each year and offer 100% of researchers within their Faculty the opportunity to raise/escalate issues | 2023-07-01 | Researchers |  |  | New
ECR2 | Ensure they act in accordance with employer and funder policies related to research integrity, and equality, diversity and inclusion | 1. Researchers to proactively seek out policies, and undertake training related to, research integrity, and equality, diversity and inclusion. | 50% of researchers to demonstrate in CEDARS in 2021 that they have understanding of Athena Swan (up from 46%), Concordat to Support the Career Development of Researchers (up from 11%) and Race Equality Charter (up from 11%). | 2022-07-01 | Researchers |  |  | P5.3
ECR3 | Take positive action towards maintaining their wellbeing and mental health | 1. Researchers to utilise institutional resources, the RSA and beyond, in order to enable positive action in relation to their wellbeing and mental health | The RSA, working with the Head of Health, Safety & Wellbeing, to identify one case study per year of a researcher who has utilised these resources to develop an alternative career path - to be published on the central hub. | 2023-07-01 | Researchers |  |  | New
ECR4 | Use available mechanisms to report staff who fail to meet the expected standards of behaviour, particularly in relation to discrimination, harassment, bullying, and research misconduct | 1. Researchers to proactively utilise mechanisms available internally to address standards of behaviour which fall below expectations. | RSA to develop an annual case study highlighting how formal mechanisms have been used effectively to improve working conditions for researchers. To be published on the Research Hub. | 2023-07-01 | Researchers |  |  | P6.9
ECR5 | Consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | Undertake annual analysis of how researchers have fed into FRPPC and URPPC to influence policy development. | Minutes of FRPPC and URPPC meetings to demonstrate how researchers have fed into policy development. | 2023-07-01 | Researchers |  |  | P3.13
Employment
Institutions must:
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices | 1. Continue to ensure that all selection panel chairs have completed BU Recruitment & Selection training which includes bias awareness, fairness and equity , etc 2. Undertake an annual survey of new research staff seeking their feedback on the selection and appointment process 3. Review advertisements to ensure that they are as inclusive and balanced to encourage a diverse applicant pool 4. Implement the e-Recruitment module and undertake monitoring to ensure interview panels reflect diversity and experience/expertise 5. Revise and launch new and updated professional development for recruiting managers which includes significant insights into diversity and equality, including the importance and benefits of an inclusive workforce | 1. Implementation and compliance with panel composition and mandatory training requirements 2. Implement and establish a baseline response rate to the new starter survey 3. Report annual survey response to RSCG and identify any appropriate actions 4. Relaunch Recruitment and Selection professional development for managers | 2025-07-01 | HR Senior Manager |  |  | P1.2 P6.2 P6.7
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position | 1. To develop better support for Faculty/Departmental induction of academic and research staff. 2. Develop a BU mentor network so that all researchers have at least 1 suitable mentor who is separate from their line manager | 1. 80% of researchers (up from 77% in CROS19) to have attended a Faculty/Departmental induction and 70% to report this as being useful (up from 47%) 2. Evidence that a mentor network has been created and all researchers have been sign posted to relevant BU colleague. See an increase from 8% (CROS19) to 50% (CEDARS). | Jul-23 | Senior RDS Manager |  |  | P3.6
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances | 1. Review the Probation approach for Research staff (reflection their role as academics, not professional service staff) 2. Faculties to review development opportunities for research staff as part of their succession planning and talent management activity 3. To seek to develop and implement a research staff career pathway | 1. Undertake research (through focus groups) with researchers to garner greater insight into the probation approach 2. Updated Probation approach to be delivered 3. Researcher career pathway to be updated | 2023-07-01 | RDS, DDRPP, HR&OD |  |  | P2.6 P6.3 P6.4 P6.7
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent | Provision of training in effective line/project management for those with direct reports including research staff. | In CEDARS, 25% of researcher leaders to say they would benefit from more development on managing staff performance (down from 59%) and 30% to say they would benefit from more training on project finances (down from 66%). | 2022-08-01 | HR Senior Manager |  |  | P2.3
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation | 1. Ensure managers of research staff fully understand, and are able to undertake, the role. 2. Ensure consistency of approach to the management of research staff. 3. Ensure that Faculties monitor appraisals ensuring that research staff have annual appraisals and personal and professional development plans in place . | 1. OD to arrange a Supporting Induction & Probation session, targeted at managers of research staff, 50% of staff to have attended. 2. Promote use of PPDP/Appraisal Brightspace resources by managers of research staff - 100% to have received appropriate resources. 3. At least 75% of research staff to have received an appraisal including objective setting and development conversations as evidenced by Faculties, and 80% to have found it useful (CEDARS). | 2022-08-01 | HR Senior Manager |  |  | P2.6 P6.3 P6.4
EI5 | Related to above | 1. Continue with workforce planning conversations and provision of relevant people metrics for Faculties to undertake succession planning and redeployment for research staff. 2. Review the Code of Practice for the Employment and Development of Research Staff and procedural guidance on probation, and appraisal for research staff to ensure it is clear to follow and consistently applied across all Faculties. | 1. Ensure senior academics undertake and have access to management of fixed term contracts, recruitment and workforce planning and talent, performance and succession development. To be evidenced by the reduction in the number of Research Staff on fixed term contracts from 86% by 50%. | 2025-08-01 | HR Senior Manager
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress | 1. To monitor and understanding the impact of COVID-19 on researcher contracts and seek to mitigate early cessation through use of Bridging Fund 2. Through work force planning proactively seek to reduce uncertainty for staff on fixed term contracts through early intervention and identification of options (extension, new project, etc) 3. Faculties to use work force planning to inform their workforce decisions in order to create greater stability | 1. Research managers offered development in respect of management of fixed term contracts, redeployment and career development 2. Ensure that 100% of research staff are in employment and research ready, if this employment is within BU or elsewhere 3. Bridging Fund highlighted to Researchers and Managers at regular intervals (12/9/6/3 months) prior to planned expiry date | 2022-08-01 | HR Senior Manager |  |  | P1.3 P2.1 P2.2
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making | 1. To support and resource the RSA and to strengthen links with other BU staff/departments 2.To ensure research staff have, and know they have, a voice at URPPC, FRPPCs and RCSG. 3. To survey the RSA constituency to understand the types of activities that will interest and engage them, and build this into the RSA’s plan of activities. 4. Create opportunities for researchers to profile their research activities within senior management teams | 1. 75% of active RSA members to report strengthened links with other BU staff/departments 2. Ensure that research staff input is minuted at formal committees; and that these are circulated through research staff. 3. Undertake an annual survey and consult reps at the steering group as to appropriate survey. Evidence that these have been incorporated. 4. To have ensured that researchers have had opportunities to present to FRPPCs, URPPC and strategic research development groups. | 2021-09-01 | Senior RDS Manager |  |  | P3.13
Funders must:
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies | N/A | N/A | N/A | N/A |  |  | P2.4
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security | N/A | N/A | N/A | N/A |  |  | New
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression | N/A | N/A | N/A | N/A |  |  | P2.4
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels | N/A | N/A | N/A | N/A |  |  | New
Managers of researchers must:
EM1 | Undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care | 1. Managers of researchers to undertake relevant training opportunities to effectively manage researchers. | See EI4, EI5 | 2022-07-01 | HoDs/line managers of researchers |  |  | P2.3
EM2 | Familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding | 1. Managers of researchers undertake relevant training with regards to relevant legislation, practice and policies, including T&Cs on grant funding. | 75% of colleagues to have undertaken the relevant training and minimal number of breaches reported. | 2022-07-01 | HoDs/line managers of researchers |  |  | P2.2
EM3 | Commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers | See EI3 | Implementation of a career framework | 2022-12-01 | HoDs/line managers of researchers |  |  | P6.3
EM4 | Actively engage in regular constructive performance management with their researchers | Managers of research to undertake monthly one to one meetings, which include appropriate review of performance against appraisal objectives | RSA representatives to report to the RSCG quarterly meeting the extent to which this objective is being met | 2021-07-01 | HoDs/line managers of researchers |  |  | P2.3
EM5 | Engage with opportunities to contribute to relevant policy development within their institution | Managers of researchers to encourage researchers to contribute to institute policy development where opportunities to arise. | RSA representatives to report to the RSCG examples of when researchers have fed into policy development | 2022-07-01 | HoDs/line managers of researchers |  |  | New
Researchers must:
ER1 | Ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder | 1. Researchers to embrace working within relevant policies, procedures and legislation and their funder requirements. | No registered breeches occurring. | 2022-07-01 | Researchers |  |  | New
ER2 | Understand their reporting obligations and responsibilities | 1. Researchers to work with their line managers, senior managers and central research office to ensure they understand and adhere to reporting obligations and responsibilities] | No breeches occurring. | 2022-07-01 | Researchers |  |  | New
ER3 | Positively engage with performance management discussions and reviews with their managers | Researchers to positively embrace the opportunities to review performance with management teams. | 50% of researchers reporting in CEDARS21 they are regularly undertaking performance management reviews, up from 32% in 2019. | 2021-07-01 | Researchers |  |  | P5.6
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community | Researchers to recognise their role as stakeholders and act positively on this | 50% of researchers to undertaken 1 or more development opportunities (offered through the RKEDF, RSA etc) each year. | 2022-07-01 | Researchers |  |  | P5.2
Professional and Career Development
Institutions must:
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors | 1. To continue to provide a comprehensive training programme across the academic year relevant to researcher orientation, funding acquisition, managing research projects and teams, and impact and knowledge exchange, with sufficient places so that each researcher (academic or otherwise) could have 10 days of training per person. 2. To ensure that research staff have the same access to this training as other staff, by providing research staff the same information about research training and support as academic staff - on starting and at induction and via BU blogs, intranet and other forums (e.g. the Early Career Researchers Network and the Research Staff Association). 3. To provide managers of research staff information about the research training and support their member of staff is entitled to when they start in their role. 4. To monitor attendance of training courses to be able to analyse and report on whether the minimum number of training days per member of staff is being met. This will require identifying whether or not an attendee is a member of the research staff. | 1. Provide sufficient volume of training activities aligning to the Vitae RDF, for researchers to undertake a minimum of 10 days training opportunities per year. 2. 100% of applicable training opportunities to be open to researchers and for these to be cross promoted through the ECRN/RSA. 3. 100% of HoDs, DHoD and DDRPPs to receive details of the training opportunities available annually and for this to be included within new starter induction packs 4. To produce an annual report monitoring attendance at institutional training. | 2021-12-01 | RDS (Funding Development Manager) |  |  | P3.1 P3.3 P5.5
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers | 1. To improve workforce planning and information to Faculties for the proactive management of succession planning and redeployment for research staff. This would support talent retention and career security. 2. Target appropriate research leaders and managers and encourage them to participate in training and development. | 1. 75% Senior academics leaders to have participated in the forthcoming Talent, Performance and Succession Programme 2. CEDARS results to increase the number of researchers with a career development plan from 57% in 2019 to 75%. | 2022-12-01 | HoDs/line managers of researchers |  |  | P3.10
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers | 1. Regularly advertise careers advice services available directly to research staff 2. Provide documentation on research staff career pathways. 3. Facilitate external mentorship with researchers who have pursued non-academic careers | 1. Highlight careers service to researchers each quarter, with a minimum of one consultation taking place. 2. Publish two case studies per annum detailing career development of researchers in academic and non-academic career paths 3. Broker two mentor/mentee relationships per year | 2022-12-01 | Head of Leadership & Talent Management |  |  | P3.1
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills | 1. Clarify institutional expectation that - inline with the concordat - researchers will have the opportunity to develop their research identify and broader leadership skills | 1. The average number of days of training undertaken by researchers to increase from an average of 3.6 (CROS19) to 7. | 2022-12-01 | HR Senior Manager |  |  | P3.11 P3.14
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this | 1. Offer workshops on how to change career paths between academia and other industries. 2. Facilitate external mentorships with researchers who have pursued non-academic careers. | 1. Offer two workshops per year on how to develop your career as a researcher within and beyond academia. 2. Broker two mentor/mentee relationships per year. | 2021-12-01 | Careers Service (Careers Adviser) and Doctoral College (Research Skills and Development Officer) |  |  | P3.2 P3.4
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities, and researcher career development reviews | 1. Identify how existing central data sources / systems can monitor and report on this action 2. Run an annual focus groups with researchers, and with managers, to explore the extent of engagement and barriers to progress | 1. Production of an annual report of centrally collated information to be presented at the RCSG to inform future action planning 2. Report thematic analysis of focus groups to RCSG to inform future action planning | 2021-12-01 | Head of Leadership & Talent Management |  |  | New
Funders must:
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning | N/A | N/A | N/A | N/A |  |  | P3.7 P3.9
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes | N/A | N/A | N/A | N/A |  |  | New
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit | N/A | N/A | N/A | N/A |  |  | New
Managers of researchers must:
PCDM1 | Engage in regular career development discussions with their researchers, including holding a career development review at least annually | 1. Line managers to ensure that they undertake annual formal appraisal an interim appraisal with researchers that include discussion around career development. 2. Line managers of researchers to have undertaken relevant internal training on how to support/enable the career development of researchers. 3. URPPC to discuss on an annual basis to review progress of the development of researcher careers and agree actions to promote cross-institutional culture change. | 1. 75% of researchers to have received an appraisal (up from 32% in CROS19) and over 80% to have found it useful (up from 67% in CROS2019). 2. 100% of line managers to have been offered relevant training. 3. URPPC to review progress on an annual basis and agree actions on how cultural change can be accelerated. | 2022-09-01 | HoDs/line managers of researchers |  |  | P2.3
PCDM2 | Support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments | 1. Line managers to ensure that researchers are aware of the mentor allocated to them and ensure it is an active relationship. 2. Ensure that researchers access the central careers guidance available to them. | 1. See a rise in the number of researchers meeting a mentor, from 8% (CROS19) to 50%. 2. See an annual increase in the number of researchers accessing the careers service by 10% each year. | 2023-07-01 | HoDs/line managers of researchers |  |  | P3.4 P3.8 P5.5
PCDM3 | Allocate a minimum of 10 days pro rata, per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development | 1. All line managers of researchers to ensure researchers are empowered to spend 10 days per year on professional development, as a minimum. Activities to include formal training e.g. through the RKEDF, work experience or external training opportunities. Time, for example, to write publications, should not be included within this allocation. | 1. The average number of days of training undertaken by researchers to increase from an average of 3.6 (CROS19) to 7. | 2023-12-01 | HoDs/line managers of researchers |  |  | New
PCDM4 | Identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours | 1. All line managers of researchers to empower their staff to develop their research identity/leadership skills through activities including writing publications, convening academic events (such departmental seminars) etc., as part of their day-to-day duties outside of their formal professional development allocation. | 1. The RSA to report quarterly to the RCSG feedback on the extent to researchers are empowered to do this at a local level. 2. See a rise in the number of researchers meeting a mentor, from 8% (CROS19) to 50%. | 2023-12-01 | HoDs/line managers of researchers |  |  | P3.6 P3.9 P5.5
PCDM5 | Engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development | 1. All academic line managers to undertake appropriate training 2. Include performance management and development in both leadership and management development. | 1. CEDARS survey to report that 60% of academic staff have undertaken BU leadership programmes (up from 45% in CROS19). | 2023-12-01 | HoDs/line managers of researchers |  |  | New
Researchers must:
PCDR1 | Take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year | 1. Researchers to engage positively with their professional development | 1. The average number of days of training undertaken by researchers to increase from an average of 3.6 (CROS19) to 7. 2. See a rise in the number of researchers meeting a mentor, from 8% (CROS19) to 50%. | 2022-07-01 | Researchers |  |  | P5.5
PCDR2 | Explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments | 1. Researchers to engage positively with opportunities to develop a range of future employment options | 1. See a rise in the number of researchers meeting a mentor, from 8% (CROS19) to 50%. 2. Establish a mechanisms for recording the number of researchers engaging with the careers service and secure a growth in this number. | 2022-07-01 | Researchers |  |  | P3.8
PCDR3 | Maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications | 1. Researchers to ensure they develop and maintain a PPDP as part of their annual appraisal process. | 75% of researchers to report in the annual institutional survey/CEDARS that they have a PPDP | 2022-07-01 | Researchers |  |  | P5.5
PCDR4 | Positively engage in career development reviews with their managers | 1. Researchers to positively engagement in career development reviews with their managers. | 75% of researchers to report they are positively engaging with performance reviews | 2022-07-01 | Researchers |  |  | P3.10
PCDR5 | Seek out, and engage with, opportunities to develop their research identity and broader leadership skills | 1. Researchers to take responsibility for developing their research identity and leadership skills | 1. 90% of respondents to CROS to report that they have taken ownership of their career development (up from 86% in CROS19) 2. 50% of respondents to CROS to report that they have undertaken leadership training (up from 14% in 2019) | 2022-07-01 | Researchers |  |  | P5.5
PCDR6 | Consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation | 1. Researchers to take responsibilities for developing their experience of the wider research experience | 1. See an increase the number of researchers reporting they have undertake training across the research system (up from an average of 23% in CROS19 to 50%). | 2022-07-01 | Researchers |  |  | P5.2
* The Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.

## Acronyms
ACF – Academic Career Framework
ADD - Academic Development and Diversity
ACORN Fund - Acceleration of Research and Networking
ATRS - Academic Targeted Research Scheme
CE Mark - Conformité Européene
CEDARS - Culture, Employment and Development in Academic Research Survey
CoP - Code of Practice
CROS - Careers in Research Online Survey
DDRPP - Deputy Dean for Research & Professional Practice
DHoDs - Deputy Heads of Department
ECR - Early Career Researcher
ECRN - Early Career Researchers Network
EDI - Equality, Diversity, Inclusion
ESRC – Economic and Social Research Council
FRPPC - Faculty Research and Professional Practice Committee
FTC - Fixed Term Contract
FTE - Full-Time Equivalent
FST - Faculty of Science and Technology
HE-BCI - Higher education and Community Interaction
HoDs - Heads of Department
HR - Human Resources
HREiR - HR Excellence in Research Award
HROD - HR and Organisational Development
IMIV - Institute of Medical Imaging & Visualisation
IMSET - Institute for the Modelling of Socio-Environmental Transitions
IP - Intellectual Property
KPI - Key Performance Indicators
MI (suite) – Management Information
OD - Organisational Development
PE - Public Engagement
PER - Public Engagement in Research
PGR - Post Graduate Researcher
PDRA - Post Doctoral Research Assistant
PIRLS - Principal Investigators and Research Leaders Survey
PPDP - Personal Professional Development Plan
RCSG - Research Concordat Steering Group
RDF - Researcher Development Framework
ResearchPAD - Platform where PGRs document supervision
RKEDF - Research & Knowledge Exchange Framework
RA - Research Assistant
RCM - Research Commercialisation Manager
RDS - Research Development & Support
REC - Race Equality Charter
RI - Research Institute
RPMC - Research Performance Management Committee
RSA - Research Staff Association
SIA - Strategic Investment Area
STEAMLab - Science, Technology, Engineering, Arts , Maths Laboratory
SUMAC - Mentoring platform/company
ToRs - Terms of Reference
TU - Trade Union
ULT - University Leadership Team
UREC - University Research Ethics Committee
URPPC - University Research & Professional Practice Committee
VLE - Virtual Learning Environment
WFP – Work Force Planning